## Projects
id | parent_id | type | name | category | scope | description | role | tech | start | end | date_source | status | progress | commits | location | highlights | links | notes
thermynx |  | project | THERMYNX — HVAC AI Operations Intelligence | HVAC Platform | Graylinx | AI-powered HVAC analytics POC for the Unicharm facility — local LLM, RAG, work orders and analytics. | Sole engineer — full-stack build: FastAPI backend, React/TypeScript frontend, Ollama integration, analytics engine. | Python; FastAPI; React; TypeScript; Ollama; MySQL; Vite | 2026-05-08 | ongoing | git | Active | 70 | 359 | D:\Harshan\HVAC AI Operations Intelligence Platform | Most active project — 308 commits; 18 feature pages + 6 Claude/LLM agents; RAG over facility docs, work-order workflow, analytics engine; Local on-prem LLM (Ollama) inference
thermynx.1 | thermynx | milestone | 18 feature pages | HVAC Platform | Graylinx | Frontend feature surface |  |  | 2026-05-08 | 2026-05-16 | git | Active | 80 | 0
thermynx.2 | thermynx | milestone | 6 AI agents | HVAC Platform | Graylinx | Claude/LLM agents |  |  | 2026-05-16 | 2026-05-24 | git | Active | 70 | 0
thermynx.3 | thermynx | milestone | RAG pipeline | HVAC Platform | Graylinx | Retrieval over facility docs |  |  | 2026-05-24 | 2026-06-01 | git | Active | 65 | 0
thermynx.4 | thermynx | milestone | Work orders | HVAC Platform | Graylinx | Work-order workflow |  |  | 2026-06-01 | 2026-06-09 | git | Active | 60 | 0
thermynx.5 | thermynx | milestone | Analytics engine | HVAC Platform | Graylinx | Chiller/HVAC analytics |  |  | 2026-06-09 | 2026-06-18 | git | Active | 60 | 0
climastream |  | project | ClimaStream — Real-time HVAC Pipeline | HVAC Platform | Graylinx | Production-grade streaming pipeline POC: Kafka -> TimescaleDB -> Airflow -> FastAPI -> Next.js. | Sole engineer — designed and built the end-to-end microservice pipeline and simulator. | Python; Kafka; TimescaleDB; Airflow; Next.js; Docker | 2026-04-24 | 2026-06-15 | git | Done | 100 | 32 | D:\Harshan\clima-stream-hvac | Proved the real-time streaming architecture; Microservices: simulator, ingestion, processor, ML, storage, API; 31 commits over ~4 weeks
climastream.1 | climastream | milestone | Device simulator | HVAC Platform | Graylinx | Synthetic HVAC data |  |  | 2026-04-24 | 2026-05-04 | git | Done | 100 | 0
climastream.2 | climastream | milestone | Kafka ingestion | HVAC Platform | Graylinx | Streaming ingest |  |  | 2026-05-04 | 2026-05-14 | git | Done | 100 | 0
climastream.3 | climastream | milestone | TimescaleDB storage | HVAC Platform | Graylinx | Time-series store |  |  | 2026-05-14 | 2026-05-25 | git | Done | 100 | 0
climastream.4 | climastream | milestone | ML scoring | HVAC Platform | Graylinx | Anomaly/score service |  |  | 2026-05-25 | 2026-06-04 | git | Done | 100 | 0
climastream.5 | climastream | milestone | Next.js UI | HVAC Platform | Graylinx | Frontend dashboard |  |  | 2026-06-04 | 2026-06-15 | git | Done | 100 | 0
omnyx |  | project | OMNYX — Universal IoT Operations Platform | HVAC Platform | Graylinx | Next-gen production platform vision: Digital-Twin FDD, RL optimization, Agentic AI, dual-database architecture. | Architecture & platform design — the strategic north star consolidating the POCs. | Python; React; TypeScript; PostgreSQL; TimescaleDB; Kafka | 2026-05-25 | ongoing | git | Active | 35 | 219 | D:\Harshan\graylinx-v2 | Digital Twin fault detection & diagnostics (FDD); Reinforcement-learning optimization; Agentic AI operations layer; Dual-DB (PostgreSQL + TimescaleDB) design
omnyx.1 | omnyx | milestone | Digital-Twin FDD | HVAC Platform | Graylinx | Fault detection & diagnostics |  |  | 2026-05-25 | 2026-05-30 | git | Active | 40 | 0
omnyx.2 | omnyx | milestone | RL optimization | HVAC Platform | Graylinx | Setpoint optimization |  |  | 2026-05-30 | 2026-06-04 | git | Planned | 15 | 0
omnyx.3 | omnyx | milestone | Agentic AI | HVAC Platform | Graylinx | Operations agents |  |  | 2026-06-04 | 2026-06-09 | git | Active | 30 | 0
omnyx.4 | omnyx | milestone | Dual-DB architecture | HVAC Platform | Graylinx | Postgres + Timescale |  |  | 2026-06-09 | 2026-06-15 | git | Active | 45 | 0
gl-pulse |  | project | GL Pulse — Platform Architecture | HVAC Platform | Graylinx | Reference architecture & planning docs unifying ClimaStream, THERMYNX and OMNYX into one next-gen vision. | Author — architecture documentation and lessons-learned consolidation. | Markdown; Architecture | 2026-05-26 | 2026-05-30 | approx | Ongoing | 60 | 0 | D:\Harshan\gl-pulse | 20 architecture documents; Consolidates POC lessons into unified design
gl-pbs |  | project | GL PBS / BACnet Simulation | HVAC Platform | Graylinx | BACnet device simulator workstream (simulator dashboard lives under Current Works in GL). | Simulation flow study and BACnet device/UI analysis. | Vue 3; BACnet; Simulation | 2026-05-11 | 2026-05-13 | manual | Paused | 20 | 0 | D:\Harshan\gl-pbs-simulation | BACnet device simulation; Vue 3 simulator dashboard
current-works |  | project | Current Works in GL — Core Monorepo | Graylinx Core | Graylinx | Active Graylinx monorepo: backend/frontend, commission tool, ML trainings, simulations, Kafka stress testing. | Sole engineer — Kafka performance testing, cross-machine benchmarking, DB/ETL architecture audits. | Node.js; Express; Kafka; MySQL; Python | 2026-06-04 | 2026-06-04 | git | Active | 75 | 16 | D:\Harshan\Current Works in GL | Kafka stress tests 150x -> 5000x scale; Cross-machine 24GB vs 8GB comparison reports; DB & ETL critical-flaws audits, management summaries
current-works.1 | current-works | milestone | Kafka stress tests (150x-5000x) | Graylinx Core | Graylinx | Throughput scaling |  |  | 2026-06-04 | 2026-06-04 | git | Active | 80 | 0
current-works.2 | current-works | milestone | Cross-machine 24GB vs 8GB | Graylinx Core | Graylinx | Hardware comparison |  |  | 2026-06-04 | 2026-06-04 | git | Done | 100 | 0
current-works.3 | current-works | milestone | DB/ETL architecture audits | Graylinx Core | Graylinx | Critical-flaws reviews |  |  | 2026-06-04 | 2026-06-04 | git | Active | 70 | 0
docs |  | project | Graylinx Docs & PRD | Graylinx Core | Graylinx | Product/architecture documentation: PRD, Modules & Features (175 features), Kafka/stress reports. | Author/maintainer — PRD, feature inventory, architecture references. | Markdown; PRD; Documentation | 2026-04-28 | 2026-05-21 | approx | Ongoing | 65 | 0 | D:\Harshan\Docs | Graylinx_Modules_and_Features.md — 175 features, phased; PRD v1.0 + Industrial Platform Master
selfaware-suite |  | project | The SelfAware® Intelligence Suite | SelfAware Suite | Personal | Six-product local-AI suite (6 repos): Continuum (HVAC intelligence), AuditShield, Autonomous-Cortex, NeuralPulse, VisioScan, SpatialNexus. | Designed & built the multi-product suite across six repositories. | React; TypeScript; Python; Neo4j; pgvector; Ollama; Docker | 2026-05-18 | 2026-05-21 | git | Active | 45 | 94 | D:\Harshan\The SelfAware® Intelligence Suite | 6 products in one suite; SelfAware Continuum: Unicharm + Neo4j + pgvector + Ollama
selfaware-suite.1 | selfaware-suite | milestone | SelfAware Continuum — HVAC intelligence | SelfAware Suite | Personal | Neo4j + pgvector + Ollama |  |  | 2026-05-18 | 2026-05-18 | git | Active | 55 | 0
selfaware-suite.2 | selfaware-suite | milestone | AuditShield — Compliance Ledger | SelfAware Suite | Personal | Compliance ledger |  |  | 2026-05-18 | 2026-05-19 | git | Done | 100 | 0
selfaware-suite.3 | selfaware-suite | milestone | Autonomous-Cortex — Mission Console | SelfAware Suite | Personal | Mission console |  |  | 2026-05-19 | 2026-05-19 | git | Done | 100 | 0
selfaware-suite.4 | selfaware-suite | milestone | NeuralPulse — Signal Lab | SelfAware Suite | Personal | Signal lab |  |  | 2026-05-19 | 2026-05-20 | git | Done | 100 | 0
selfaware-suite.5 | selfaware-suite | milestone | VisioScan — Light Studio | SelfAware Suite | Personal | Light studio |  |  | 2026-05-20 | 2026-05-20 | git | Done | 100 | 0
selfaware-suite.6 | selfaware-suite | milestone | SpatialNexus — Topology Atlas | SelfAware Suite | Personal | Topology atlas |  |  | 2026-05-20 | 2026-05-21 | git | Done | 100 | 0
farmer-app |  | project | Nesso — Farm Traceability Platform | Client Apps | Client | Farm-to-fork traceability platform for NR Group (Nesso). | Built the traceability web app — including a weekend build sprint (30–31 May). | TypeScript; React; Node.js | 2026-05-28 | ongoing | git | Active | 45 | 191 | D:\Harshan\farmer-app | Farm-to-fork traceability (NR Group); ~1-week build incl. weekend sprint
selfaware-dev-stack |  | project | SelfAware Dev Stack | Infra & Tooling | Personal | Canonical local Docker dev stack (MySQL, PostgreSQL, Neo4j, Redis) for the SelfAware products. | Authored the docker-compose environment for 4 products. | Docker; MySQL; PostgreSQL; Neo4j; Redis | 2026-05-21 | 2026-05-21 | approx | Done | 100 | 0 | D:\Harshan\selfaware-dev-stack | One dev environment for 4 products
mysql-unicharm-proxy |  | project | MySQL Unicharm Proxy (deprecated) | Infra & Tooling | Graylinx | Docker MySQL port-forwarding helper — superseded by selfaware-dev-stack. | Quick infra utility (now reference-only). | Docker; MySQL | 2026-05-21 | 2026-05-21 | approx | Done | 100 | 0 | D:\Harshan\mysql-unicharm-proxy | Deprecated — replaced by selfaware-dev-stack
python-etl |  | project | Python ETL | Infra & Tooling | Graylinx | ETL / transformer-layer workstream (planning + follow-ups in May). | ETL transformer-layer planning and conversion-workflow design. | Python; ETL | 2026-05-14 | 2026-05-25 | manual | Planned | 10 | 0 | D:\Harshan\python-etl | ETL transformer layer planning
raspberry |  | project | Raspberry Stuffs | Infra & Tooling | Personal | Raspberry Pi / edge experiments (placeholder). | Edge hardware experiments. | Raspberry Pi | 2026-06-13 | 2026-06-13 | approx | Planned | 5 | 0 | D:\Harshan\Rasberry-stuffs | Placeholder
gl-hvac-early |  | project | Graylinx.ai HVAC (early prototype) | HVAC Platform | Graylinx | "HVAC Data Pipeline v2" — first Graylinx HVAC repo (Python), precursor to ClimaStream. | Initial HVAC data-pipeline prototype. | Python | 2026-04-20 | 2026-04-21 | github | Done | 100 | 8 |  | First HVAC repo on GitHub (8 commits); Precursor to ClimaStream
gl-legacy-analysis |  | project | Graylinx Legacy-Code Analysis | Graylinx Core | Graylinx | Audit/analysis of the Graylinx legacy codebase that informed the v2/OMNYX rebuild. | Reviewed & documented legacy code for migration. | JavaScript; Node.js | 2026-04-28 | 2026-05-01 | github | Done | 100 | 7 |  | Legacy code audit (7 commits); Fed into OMNYX architecture
poc-hvac-pipeline |  | project | HVAC Data Pipeline (v1 & v2) | HVAC Platform | Graylinx | Graylinx HVAC Chiller-Plant telemetry pipeline: Node.js → MySQL + Kafka → MinIO (Parquet + manifests) → Airflow → ClickHouse → Grafana. v1 + production-ready v2 on the harshan-aiyappa account (Nov 2025). | Built the end-to-end pipeline + its 3 POCs with J. Suryanarayanan & Satish Krishna; milestone-tracked over email. | Node.js; Express; Kafka; MinIO; Parquet; Airflow; ClickHouse; Grafana; Python; Docker | 2025-11-19 | 2025-11-26 | github | Done | 100 | 12 |  | Chiller-plant predictive-maintenance + energy-optimization pipeline; v1 (19 Nov) + production v2 (26 Nov 2025), harshan-aiyappa account; POCs: Ingestion · Data Lake · Analytics
poc-hvac-pipeline.1 | poc-hvac-pipeline | milestone | POC 1 — Ingestion (Node.js → MySQL + Kafka) | HVAC Platform | Graylinx | Simulator → Node.js service → MySQL + Kafka |  |  | 2025-11-19 | 2025-11-21 | github | Done | 100 | 0
poc-hvac-pipeline.2 | poc-hvac-pipeline | milestone | POC 2 — Data Lake (Kafka → MinIO/Parquet) | HVAC Platform | Graylinx | Kafka → connector → MinIO Parquet storage |  |  | 2025-11-21 | 2025-11-23 | github | Done | 100 | 0
poc-hvac-pipeline.3 | poc-hvac-pipeline | milestone | POC 3 — Analytics (Airflow → ClickHouse → Grafana) | HVAC Platform | Graylinx | MinIO → Airflow → ClickHouse → Grafana dashboards |  |  | 2025-11-23 | 2025-11-26 | github | Done | 100 | 0

## Engagement
date | day | work_type | location | hotel | check_in | check_out | travel | notes | linked_project | source | communications
2026-04-22 | Wednesday | Discussion | Graylinx Office Bangalore |  | 11:00 AM | 2:00 PM | Mysore to Bangalore and return | Initial deployment and coordination discussion with Graylinx team | current-works | csv
2026-04-23 | Thursday | WFH | Mysore |  |  |  |  | Lingotran task + recruitment interviews for RAPL and Examic. |  | manual
2026-04-24 | Friday | WFH | Mysore |  |  |  |  | Lingotran task + recruitment interviews for RAPL and Examic. |  | manual
2026-04-25 | Saturday | WFH | Mysore |  |  |  |  | Lingotran task + recruitment interviews for RAPL and Examic. |  | manual
2026-04-26 | Sunday | WFH | Mysore |  |  |  |  | Lingotran task + recruitment interviews for RAPL and Examic. |  | manual
2026-04-27 | Monday | Office | Graylinx Office Bangalore | GRS Hotel | 9:30 AM | 6:30 PM | Mysore to Bangalore | Started office deployment and stayed at hotel near office | current-works | csv
2026-04-28 | Tuesday | Office | Graylinx Office Bangalore | GRS Hotel | 9:30 AM | 6:30 PM | Stayed in Bangalore | Continued office work and architecture discussions | current-works | csv | Vishnu Ranga (3) — Gents Bangalore
2026-04-29 | Wednesday | Office | Graylinx Office Bangalore | GRS Hotel | 9:30 AM | 6:30 PM | Stayed in Bangalore | Regular office work and coordination discussions | current-works | csv
2026-04-30 | Thursday | Office | Graylinx Office Bangalore | GRS Hotel | 9:30 AM | 6:30 PM | Bangalore to Mysore | Returned to Mysore due to Friday leave |  | csv | Nirali Patel (27) — Backend / DB · Santosh (2) — Analytics
2026-05-01 | Friday | Leave | Mysore |  | Leave | Leave | Stayed in Mysore | Friday leave and rest day |  | csv | Nirali Patel (17) — Backend / DB
2026-05-02 | Saturday | WFH | Mysore |  |  |  |  | Lingotran task + recruitment interviews for RAPL and Examic. |  | manual
2026-05-03 | Sunday | WFH | Mysore |  |  |  |  | Lingotran task + recruitment interviews for RAPL and Examic. |  | manual | Nirali Patel (1) — Access Attachment
2026-05-04 | Monday | Discussion | NA Group Office Mysore |  | 10:00 AM | 6:00 PM | Local travel within Mysore | PRD discussion regarding HVAC systems and architecture modules with Vishnu | omnyx | csv | Nirali Patel (9) — Backend / DB, Planning / sync · Vishnu Ranga (3) — Cloudops Docx
2026-05-05 | Tuesday | Discussion | NA Group Office Mysore |  | 10:00 AM | 6:00 PM | Local travel within Mysore | Continued PRD planning and module discussions | omnyx | csv | Nirali Patel (59) — Backend / DB, Planning / sync · Vishnu Ranga (7) — Telemetry / sensing, Deployment
2026-05-06 | Wednesday | Discussion | NA Group Office Mysore |  | 10:00 AM | 6:00 PM | Local travel within Mysore | Finalized PRD discussions and architecture workflows | omnyx | csv
2026-05-07 | Thursday | WFH | Mysore |  |  |  |  | Lingotran task + recruitment interviews for RAPL and Examic. |  | manual | Santosh (5) — Able Create
2026-05-08 | Friday | Office | Graylinx Office Bangalore | GRS Hotel | 9:30 AM | 6:30 PM | Mysore to Bangalore | Worked with Vishnu before his Australia travel and discussed ongoing tasks |  | csv | Karthik (2) — BACnet / simulation
2026-05-09 | Saturday | Office | Graylinx Office Bangalore | GRS Hotel | 9:30 AM | 6:00 PM | Bangalore to Mysore | Returned to Mysore after architecture discussions and AI demonstrations | thermynx | csv | Santosh (1) — general chat
2026-05-10 | Sunday | WFH | Mysore |  | 10:00 AM | 5:00 PM | Worked from Mysore residence | Continued assigned tasks remotely and coordinated pending work |  | csv
2026-05-11 | Monday | WFH | Mysore |  | 10:00 AM | 6:00 PM | Worked from Mysore residence | Existing BACnet simulation flow understanding discussions with team | gl-pbs | csv | Himanshu (43) — Planning / sync · Karthik (13) — BACnet / simulation
2026-05-12 | Tuesday | WFH | Mysore |  | 10:00 AM | 6:00 PM | Worked from Mysore residence | BACnet device simulation and UI analysis discussions along with recruitment coordination | gl-pbs | csv | Himanshu (16) — Hardware / cost, Backend / DB · Karthik (6) — Planning / sync · Pradeep Nagabhushana (8) — Architecture, Planning / sync · Santosh (15) — Kafka stress test, BACnet / simulation
2026-05-13 | Wednesday | WFH | Mysore |  | 10:00 AM | 6:00 PM | Worked from Mysore residence | Interface and workflow architecture study and recruitment activities | omnyx | csv | Karthik (3) — Chillers Handling · Santosh (5) — Appreciated Keep
2026-05-14 | Thursday | WFH | Mysore |  | 10:00 AM | 6:00 PM | Worked from Mysore residence | Technical coordination discussions ETL follow-ups and recruitment process handling | python-etl | csv | Himanshu (21) — Backend / DB, Planning / sync · Karthik (3) — Sheets Talk · Nirali Patel (11) — Learning Python · Pradeep Nagabhushana (12) — Better Virtually
2026-05-15 | Friday | WFH | Mysore |  | 10:00 AM | 6:00 PM | Worked from Mysore residence | Transformer layer follow-up discussions and recruitment coordination activities | python-etl | csv | Nirali Patel (2) — Server
2026-05-16 | Saturday | WFH | Mysore |  | 10:00 AM | 5:00 PM | Worked from Mysore residence | ETL and conversion workflow discussions along with interview coordination | python-etl | csv
2026-05-17 | Sunday | WFH | Mysore |  | 10:00 AM | 4:00 PM | Worked from Mysore residence | Pending task coordination architecture planning and recruitment follow-ups | current-works | csv
2026-05-18 | Monday | WFH | Mysore |  | 10:00 AM | 6:00 PM | Worked from Mysore residence | Continued ETL transformer layer planning discussions and recruitment activities | python-etl | csv | Santosh (12) — Kafka stress test, Agentic orchestration
2026-05-19 | Tuesday | WFH | Mysore |  | 10:00 AM | 6:00 PM | Worked from Mysore residence | Follow-up discussions architecture coordination and recruitment processes | current-works | csv | Santosh (17) — Deployment, Hiring / interviews
2026-05-20 | Wednesday | WFH | Mysore |  | 10:00 AM | 6:00 PM | Worked from Mysore residence | Continued ETL transformer planning pending clarifications and recruitment coordination | python-etl | csv | Pradeep Nagabhushana (19) — Planning / sync · Santosh (5) — Planning / sync
2026-05-21 | Thursday | WFH | Mysore |  | 10:00 AM | 6:00 PM | Worked from Mysore residence | Technical discussions implementation planning and interview coordination | current-works | csv | Nirali Patel (3) — Model evaluation · Pradeep Nagabhushana (11) — Kafka stress test, Agentic orchestration · Santosh (3) — Planning / sync
2026-05-22 | Friday | WFH | Mysore |  | 10:00 AM | 6:00 PM | Worked from Mysore residence | Continued project coordination follow-ups and recruitment activities | current-works | csv | Santosh (7) — Connect Later
2026-05-23 | Saturday | WFH | Mysore |  | 10:00 AM | 5:00 PM | Worked from Mysore residence | Ongoing ETL architecture planning discussions and recruitment work | python-etl | csv
2026-05-24 | Sunday | WFH | Mysore |  | 10:00 AM | 4:00 PM | Worked from Mysore residence | Pending workflow coordination architecture discussions and recruitment coordination | current-works | csv
2026-05-25 | Monday | WFH | Mysore |  | 10:00 AM | 6:00 PM | Worked from Mysore residence | Continued follow-ups project discussions and recruitment coordination | current-works | csv | Pradeep Nagabhushana (8) — Model evaluation, Deployment · Santosh (4) — Planning / sync
2026-05-26 | Tuesday | WFH | Mysore (residence) |  |  |  |  | OMNYX [9]: docs: PROJECT_OVERVIEW.md — vision, legacy comparison, transformation story; docs: ARCHITECTURE_RATIONALE.md — pros, cons, risk register, on-site scenarios; docs: align all MD docs with 2-DB architecture + Alloy/Kafka images (+6 more) (9 commits) | omnyx | derived | Pradeep Nagabhushana (18) — Kafka stress test, Agentic orchestration · Vishnu Ranga (2) — Kafka stress test, Agentic orchestration
2026-05-27 | Wednesday | WFH | Mysore (residence) |  |  |  |  | THERMYNX [1]: feat: implement full-stack HVAC AI operations platform with multi-agent orchestr (1 commits) | thermynx | derived | Anushri (5) — Telemetry / sensing · Karthik (3) — Anomalies Branch · Pradeep Nagabhushana (3) — Kafka stress test, Telemetry / sensing · Santosh (2) — GPU / VRAM sizing, Hardware / cost · Vishnu Ranga (3) — GPU / VRAM sizing, Hardware / cost
2026-05-28 | Thursday | WFH | Mysore (residence) |  |  |  |  | THERMYNX [12]: feat: add architecture documentation and configure environment-specific Claude s; docs(ai): mark Tier 1/2/3 + Perf T1 + Reliability R1/R4 + Eval Phase 1 as shippe; fix(eval+ui): action-verb regex tolerates articles + vite proxy env-driven (+9 more) · Nesso [5]: docs: add comprehensive developer setup guide and link it in README; docs: initialize README.md with project overview, architecture, and documentatio; docs: add comprehensive project implementation plan and detailed screen inventor (+2 more) (17 commits) | thermynx | derived | Anushri (1) — Telemetry / sensing, Deployment · Karthik (2) — Unicharm · Santosh (2) — BACnet / simulation · Vishnu Ranga (1) — Agentic orchestration, Model evaluation
2026-05-29 | Friday | WFH | Mysore (residence) |  |  |  |  | Nesso [8]: feat: implement activities dashboard and logging interface with API integration; feat(phase-3): crops + activities + catalog (POP + inputs) backend; feat(phase-2): web admin UI for farmers — dashboard shell, list, detail, approva (+5 more) (8 commits) | farmer-app | derived
2026-05-30 | Saturday | WFH | Mysore (residence) |  |  |  |  | Nesso [68]: feat(mobile): real in-app support + live multi-language (no more "coming soon"); fix(mobile/login): bulletproof layout + themed + add missing elements; feat(mobile): app-wide dark mode — light/dark token system + working toggles ✅ (+65 more) (68 commits) | farmer-app | derived
2026-05-31 | Sunday | WFH | Mysore (residence) |  |  |  |  | Nesso [30]: perf(P2): web chart code-split, portal OG metadata, mobile FlatList tuning; fix(mobile): revert moti from dashboard — restore stable plain View KPI cards; docs: mark Phase 6/production ON HOLD until user says (P5 banner) (+27 more) (30 commits) | farmer-app | derived
2026-06-01 | Monday | WFH | Mysore (residence) |  |  |  |  | OMNYX [40]: presentation: fix file:// security warning — embed logo as data URI; presentation: top-only navigation, no bottom nav, BOM stripped, better highlight; presentation: remove left section sidebar — full-width deck (+37 more) · Nesso [34]: feat(web-vite): MiniMap is now a real map (Leaflet+OSM, open-source, no key); docs: add INTEGRATIONS.md (APIs/CDNs/keys) + migration status; perf(web-vite): swap recharts->ECharts (tree-shaken) + lazy-load heavy routes (+31 more) · THERMYNX [10]: docs(ai): ADR for per-task LLM right-sizing decision; chore(ollama): bump MAX_LOADED_MODELS=3 + pre-warm hot set on restart; feat(ai): right-size models per task in config defaults (+7 more) (84 commits) | omnyx | derived | Anushri (48) — Telemetry / sensing, BACnet / simulation · Nirali Patel (11) — Persons Aren · Santosh (3) — BACnet / simulation
2026-06-02 | Tuesday | WFH | Mysore (residence) |  |  |  |  | OMNYX [24]: docs(dev): keep ws-bridge in Docker when running api/web locally; style(frontend): new graphite + Klein palette, WCAG AA tuned for both modes; chore(dev): park Keycloak behind phase2 profile; add local hot-reload dev workfl (+21 more) · THERMYNX [10]: docs(ai): sync AI discovery docs and update README to 2026-06-02 final state; docs: add AI discovery documentation and local development settings; docs(ai): deprioritize Grafana/Prometheus dashboard panels — metrics already emi (+7 more) · Nesso [6]: docs(testing): update roles/logins doc for Vite cutover; feat(web-vite): full shell UI/UX parity with the design; fix(web-vite): Leaflet crash + LoginPage navigate-in-render (+3 more) (40 commits) | omnyx | derived | Anushri (31) — Model evaluation, BACnet / simulation · Santosh (16) — Architecture, Planning / sync · Vishnu Ranga (6) — Kafka stress test, GPU / VRAM sizing
2026-06-03 | Wednesday | WFH | Mysore (residence) |  |  |  |  | OMNYX [55]: feat(protocols): multi-protocol DAL — MQTT + Modbus + OPC-UA adapters; feat(rag): pgvector knowledge base — ingestion + agent retrieval [Phase 2]; feat(phase2): MinIO data lake + Airflow — working telemetry archive (+52 more) · Nesso [39]: feat(mobile): preflight checker + progress logging + timeouts in dev launcher; feat(web-vite): i18n increment — localize all page titles (en/kn/hi); fix(web-vite): responsive audit — stack field grid + scroll calendar on mobile (+36 more) (94 commits) | omnyx | derived | Anushri (24) — Backend / DB, Planning / sync · Nirali Patel (1) — Check Server
2026-06-04 | Thursday | WFH | Mysore (residence) |  |  |  |  | Current Works in GL [16]: docs: add stress test summary report; docs: add Decision section to 1-page summary report; docs: update comparison and 1-page summary with all scales including 4000x and 5 (+13 more) · OMNYX [13]: docs(openapi): regenerate spec snapshots (adds /api/v1/analysis/correlation); chore: gitignore tsbuildinfo + egg-info build artifacts Co-Authored-By: Claude O; feat(analysis): device signal-correlation page + API (+10 more) · THERMYNX [6]: fix: H6+H7+H8 — forecast backend signal, agent history, is_running cast; feat(ui): work-order approve/dismiss card in agent trace (H3); fix(critical): C1+H1+H2+C3 — thread safety, tool injection, connection leak, mes (+3 more) (35 commits) | current-works | derived | Anushri (19) — Model evaluation, BACnet / simulation · Nirali Patel (2) — Leave Problem · Pradeep Nagabhushana (18) — Kafka stress test, GPU / VRAM sizing · Vishnu Ranga (5) — Kafka stress test, GPU / VRAM sizing
2026-06-05 | Friday | WFH | Mysore (residence) |  |  |  |  | OMNYX [33]: feat: real energy/efficiency KPIs from catalog semantics (Gap 1); docs(site): point onboarding/multi-tenancy/simulator docs at the generator + Mer; chore(console): cut over to Console v2 — promote frontend-next, archive legacy, (+30 more) · THERMYNX [13]: refactor(ai): consolidate prompts + share JSON parser (P1); bump NL-SQL timeout; feat(predictive): trend-based degradation -> auto-proposed PM work orders; fix(ai): reconcile kW/TR 'fair' threshold drift in prompts (+10 more) (46 commits) | omnyx | derived | Anushri (22) — Telemetry / sensing, BACnet / simulation · Pradeep Nagabhushana (19) — Agentic orchestration, Deployment
2026-06-06 | Saturday | WFH | Mysore (residence) |  |  |  |  | OMNYX [12]: docs(showcase): sync omnyx.html to delivered work; test(e2e): console v2 + reports persistence + control shadow checks; feat(console): report history/generate + RL control-actions card (+9 more) · THERMYNX [12]: feat(cmms): Phase 1C Alarm -> Work Order management; feat(ems): Phase 1B Energy Management + Cost; feat(ui): THERMYNX sibling theme — real thermal-cyan signature accent (+9 more) (24 commits) | omnyx | derived | Vishnu Ranga (2) — Agentic orchestration, Model evaluation
2026-06-07 | Sunday | WFH | Mysore (residence) |  |  |  |  | OMNYX [27]: feat: implement hvac vertical extension with agent-backed telemetry, twin predic; feat: implement initial docker-compose infra, airflow integration, and core serv; fix(security): pin RLS tenant in agentic-ai under the omnyx_svc role (+24 more) (27 commits) | omnyx | derived
2026-06-08 | Monday | WFH | Mysore (residence) |  |  |  |  | THERMYNX [14]: chore: add backend runtime logs and IDE settings configuration files; fix(ai): substitute mistral-small3.2 for phi4 — phi4-14B crashes Ollama 0.30.6; feat(ui): readable model roster + modernized 'model in use' toast (+11 more) (14 commits) | thermynx | derived | Anushri (39) — BACnet / simulation, Backend / DB · Karthik (32) — Backend / DB · Vishnu Ranga (8) — GPU / VRAM sizing, Agentic orchestration
2026-06-09 | Tuesday | WFH | Mysore (residence) |  |  |  |  | THERMYNX [6]: build(agentic): F0 — OSS agentic runtime + eval/test dependency manifests; docs(agentic): fold model-eval routing, performance must-holds, OSS-software lic; docs(agentic): framework rewrite plan, target architecture, ADR-0002, gap re-aud (+3 more) · OMNYX [1]: docs: add OMNYX project handbook and master documentation index (7 commits) | thermynx | derived | Anushri (14) — Model evaluation, Telemetry / sensing · Vishnu Ranga (9) — Agentic orchestration, Model evaluation
2026-06-10 | Wednesday | WFH | Mysore (residence) |  |  |  |  | THERMYNX [40]: feat: add custom environment settings and initial AgentRunner implementation; fix(anomaly): stop 'LLM timeout' on causal cards — warm model + headroom + keep_; chore(claude): expand tool allowlist accumulated this session (+37 more) (40 commits) | thermynx | derived | Anushri (21) — Model evaluation, Telemetry / sensing · Karthik (4) — Check Start · Vishnu Ranga (3) — GPU / VRAM sizing, Agentic orchestration
2026-06-11 | Thursday | WFH | Mysore (residence) |  |  |  |  | THERMYNX [25]: chore(obs): comment out the langfuse SDK; mark tracing disabled / future-only; chore(frontend): remove orphaned migration-leftover components (zero imports); docs(agentic): F4.9 HITL done; F1.11 durable checkpointer deferred to 48/64GB (+22 more) · OMNYX [1]: docs(ops): flag shared Ollama GPU with THERMYNX (avoid VRAM eviction) (26 commits) | thermynx | derived | Anushri (6) — Model evaluation, RAG pipeline · Vishnu Ranga (3) — GPU / VRAM sizing, Agentic orchestration
2026-06-12 | Friday | WFH | Mysore (residence) |  |  |  |  | THERMYNX [9]: docs(agentic): Session 3 handoff (2026-06-12); fix(eval): pre-push no longer auto-runs the golden suite (it floods the 20 GB GP; feat(agent): per-node timing traces (lightweight, no Langfuse/infra) (+6 more) (9 commits) | thermynx | derived | Anushri (5) — Agentic orchestration, RAG pipeline · Vishnu Ranga (3) — GPU / VRAM sizing, Agentic orchestration
2026-06-13 | Saturday | WFH | Mysore (residence) |  |  |  |  | THERMYNX [6]: docs(agentic): loop-accurate plain-English overview + incidents log + Session-4 ; feat(frontend): Agent Lab workbench - tabbed Run/History/Compare/Tune/Validate +; feat(provider): OpenRouter dev-bridge provider switch (chat roles only; embeddin (+3 more) (6 commits) | thermynx | derived | Vishnu Ranga (6) — Agentic orchestration, Architecture
2026-06-14 | Sunday | WFH | Mysore |  |  |  |  | Lingotran task + recruitment interviews for RAPL and Examic. |  | manual
2026-06-15 | Monday | WFH | Mysore (residence) |  |  |  |  | THERMYNX [24]: feat: add .claude/settings.json with pre-configured shell execution permissions; feat(security): M9 recursive injection-hardening of tool results; Add architectural handbook for Graylinx LLM platform and initialize Claude proje (+21 more) · ClimaStream [1]: docs: add architecture and agentic flow diagrams to project documentation · Nesso [1]: chore: update lockfile to reflect dependency changes · OMNYX [1]: docs: initialize architecture, security, and roadmap documentation and implement (27 commits) | thermynx | derived | Anushri (13) — Agentic orchestration, Model evaluation · Vishnu Ranga (8) — GPU / VRAM sizing, Agentic orchestration
2026-06-16 | Tuesday | WFH | Mysore (residence) |  |  |  |  | THERMYNX [14]: docs(infra): GPU cloud options + Jarvislabs setup plan to unblock Track B; docs(handoff): SESSION 6 — v3 Track-A batch + finalize IA spec; docs(plan): add plain-English v3 status (where we are / what's blocked) (+11 more) (14 commits) | thermynx | derived | Vishnu Ranga (14) — Kafka stress test, GPU / VRAM sizing
2026-06-17 | Wednesday | WFH | Mysore (residence) |  |  |  |  | THERMYNX [30]: chore: add .claude/settings.json with authorized shell commands for environment ; fix(ingest): count deleted rows via RETURNING, not result.rowcount; test(P2): unit tests for the preflight guard (action/equipment/topic gates) (+27 more) (30 commits) | thermynx | derived | Vishnu Ranga (6) — GPU / VRAM sizing, Agentic orchestration